## Sheet1
SCW Softball Club Board Action Item Log - As of 3/5/2025
Action # | Main Item | Action | Start Date | Target Date | Owner | Status
Scoreboard
SB-1 |  | Secure final approval from Rec Center and Governing Board for 25 year agreement with Liberty |  |  | Perillo/Missos | Closed
SB-2 |  | Provide Invoice for scoreboard to Liberty |  |  | Perillo | Closed - Invoice submitted
SB-3 |  | Obtain check from Liberty |  |  | Perillo | Closed - Check obtained
SB-4 |  | Obtain a contract/document from HQ Sports specifying deliverables and ETA |  |  | Missos | Closed - contract obtained
SB-5 |  | Provide initial payment to HQ Sports |  |  | McGraw/Steil | Closed - payment provided
SB-6 |  | Track progress of scoreboard manufacture and install |  | Ongoing | Sorber
Website
W-1 |  | Ensure new website is operational on all browsers |  |  | Horvath/Shuck | Closed - Website operational on all browsers
W-2 |  | Develop new member link on website for all GT participants to complete waiver, register and pay dues |  | TBD | Horvath/Shuck
W-3 |  | Update CL rules and submit for publication on Website |  |  | Derylo | Closed - posted on website
W-4 |  | "Pay Dues" page created right next to the "Home" tab at the top of the page. When clicked, take people to the actual form that needs to be completed to pay dues. |  |  | Horvath/Schuck | Closed - page created
W-5 |  | "Pay by Check" option removed and instead, add a note that says "To pay by check or cash, drop the payment in the mailbox at the field. You will be registered as having paid dues upon receipt." |  |  | Horvath/Schuck | Closed - option removed
W-6 |  | Sponsors added to the website with a link to their web page; remove the current image rotator. |  |  | Perillo | Closed - Sponsors added
W-7 |  | New player page created. Have a way to complete the waiver form online and submit electronically rather than use a fillable/printable pdf. |  | TBD | Horvath/Schuck
W-8 |  | Add Action Item Log to Website |  | TBD | Sorber/Horvath
W-9 |  | Ensure Club Calendar is accurate/up-to-date on Website |  |  | Horvath | Closed - calendar up to date
W-10 |  | On website, remove Raynor as GT contact; add Mike Currie |  |  | Czech | Closed - Raynor removed & Currie added
Concessions
C-1 |  | Develop a go-forward plan on handling concession purchases and establish new process |  |  | McGraw/Board | Closed - Plan developed and implemented
Financials
F-1 |  | Develop a standard for monthly/quarterly expense and income tracking |  |  | McGraw/Steil | Closed - Standard developed
F-2 |  | Evaluate bank accounts to determine benefits of merging accounts to one bank instead of two. |  |  | McGraw | Closed - determined that two accounts are needed
Field Maintenance
FM-1 |  | Request field maintenance team to brush turf weekly on Wednesdays |  |  | Skinner | Closed - Field brushed every other Wednesday.
FM-2 |  | Locate maintenance contract for turf maintenance |  |  | Sorber | Closed - No contract exists. Schedule once per year.
FM-3 |  | Working with Board, identify any field turf improvements. Based on these discussions, work with Rec Center (Mike Wickham) to estimate costs/schedule and then obtain Board approval. |  |  | Sorber | Turf Maintenance & Infield/Outfield transition scheduled for April 2, 2025
FM - 4 |  | Develop roles & responsibilities for Field Maintenance/Manager |  | TBD | Sorber
FM-5 |  | Evalute more frequent turf maintenance in a calendar year |  |  | Sorber | Pending - Meeting on April 2nd to address
Safety
S-1 |  | Investigate certification process for CPR/AED training |  |  | Czech | Closed - players/personnel to obtain their own CPR/AED training if desired
S-2 |  | Working with Rec Center leadership, define when/how someone is defined as a safety risk per Charter Club RRP requirement |  | TBD | Czech
S-3 |  | Improve or purchase new field first aid kit | 2025-03-05 |  | Czech
MISC
M-1 |  | Define and assign Club Roles & Responsibilities across all Board members |  | TBD | Board
M-2 |  | Define scope & charter of Marketing/Sponsorship Committee |  | TBD | Perillo | Pending - written document under development
M-3 |  | Breakout the Events/Liaison category |  | TBD | ? | Pending - Board Member liaison TBD